# LUCE — Implementation Plan

Version: 1.0

Date: October 2026

Stack: Next.js · Node.js · Firebase · Resend · Vercel · Git

## 1. Objectives

Deliver the LUCE MVP in phased modules that match academic checkpoints and PRD scope:

Auth Module — Gmail / Google enable

Clipping Module — short-form / UGC video clip generation

Transcribe Module — product extraction + caption / text pipeline

Plans / Paid Plans — Free vs Starter (and Pro) entitlements

Cross-cutting every phase: logging, error handling, unit tests, Git commits, Vercel deploys.

## 2. Phase Overview

| Phase | Module | Duration (suggest) | Outcome |
| --- | --- | --- | --- |
| 0 | Foundation | 1 week | Next.js app, Firebase project, Vercel, GitHub, DNS plan |
| 1 | Auth (Gmail) | 1–1.5 weeks | Sign-in, session, user doc, Resend welcome |
| 2 | Transcribe | 1.5–2 weeks | URL/upload → structured product → confirm UI |
| 3 | Clipping | 2 weeks | UGC/video clip jobs + Storage + results preview |
| 4 | Campaign core | 2 weeks | Research, strategy, stills/social/ads orchestration |
| 5 | Plans / Paid | 1–1.5 weeks | Quotas, billing UI, upgrade emails |
| 6 | Hardening | 1 week | Logging/errors/tests, ZIP export, DNS cutover |

Phases 2–3 can partially overlap after Auth is stable.

## 3. Phase 0 — Foundation

Tasks

☐ Create Next.js (TypeScript) app structure (marketing / + /app routes)

☐ Connect GitHub repo; protect main

☐ Create Firebase project (Auth, Firestore, Storage)

☐ Configure Vercel project + env vars

☐ Document DNS A/CNAME steps for custom domain

☐ Add base logger utility + error code map

☐ CI: lint + unit test + build

Exit criteria: Preview deploy succeeds; empty authenticated shell loads.

## 4. Phase 1 — Auth Module (Gmail Enable)

Goal: Users sign in with Google (Gmail) and optional email/password.

Tasks

☐ Enable Google provider in Firebase Auth

☐ /login, /signup UI (brand-aligned)

☐ Persist users/{uid} on first login (plan: free)

☐ Protect /dashboard and campaign routes

☐ Resend welcome email

☐ Unit tests: auth helper mocks, route guard

☐ Logs: module=auth login success/fail

Exit criteria: Google login → dashboard; logout clears session; unauthorized API returns 401.

## 5. Phase 2 — Transcribe Module

Goal: Turn product URL or images into confirmed structured product data (and later video captions).

Tasks

☐ API: ingest URL or multipart images

☐ Extract/normalize name, description, features, category, price, images

☐ Missing-field detector + smart questions seed

☐ Confirm product UI (/campaigns/[id]/confirm)

☐ Save products/{id} + source blobs

☐ Unit tests: normalize, missing fields, error codes for bad URL

☐ Logs: module=transcribe start/success/fail with requestId

Exit criteria: User can confirm a product from URL or upload; invalid URL offers manual path.

## 6. Phase 3 — Clipping Module

Goal: Generate product-faithful short video / UGC-style clips into Storage and attach to campaign.

Tasks

☐ Job enqueue for ugc_video / reels_video / marketing_video

☐ Node worker/route calls video generation provider

☐ Write MP4 + thumbnail to Storage; assets docs

☐ Results UI preview + regenerate

☐ Enforce fidelity constraints in prompts (change scene, not product)

☐ Unit tests: job mapper, status transitions, plan gate stub

☐ Logs: module=clipping per attempt

Exit criteria: At least one clip type generates, plays in results, stores under user path.

## 7. Phase 4 — Campaign Core (Research → Strategy → Full pack)

Goal: Complete PRD loop beyond clipping/transcribe.

Tasks

☐ Research summary generation + display

☐ Strategy document generation + approve

☐ Still visuals + social copy + ad creative pipelines

☐ Progress UI stages (PRD list)

☐ ZIP export (exports/campaign.zip) + download page

☐ Dashboard list of campaigns

Exit criteria: End-to-end Free user path: create → confirm → generate → download.

## 8. Phase 5 — Plans / Paid Plans

Goal: Enforce Free vs Starter (and Pro) per PRD.

Tasks

☐ Plan catalog in config + users.plan

☐ usage/{uid}_{yyyy_mm} counters

☐ Server-side block when over limit

☐ /billing UI + upgrade CTAs

☐ Resend: upgrade confirmation + limit notice

☐ Gate Agent refine to Starter+

☐ Unit tests: quota math 100%

Exit criteria: Free user blocked at limit with clear upgrade path; Starter can refine.

## 9. Phase 6 — Hardening & Launch

Tasks

☐ Structured logging review across modules

☐ Error UX pass + retry buttons

☐ Unit test suite green in CI (≥ agreed coverage)

☐ Security rules review (Firestore + Storage)

☐ Custom domain A-record cutover + SSL verify

☐ Production smoke on Vercel

## 10. Team / Role Split (suggested)

| Role | Focus |
| --- | --- |
| Frontend | Next.js pages, design system, progress UX |
| Backend | Node APIs, jobs, ZIP, Resend |
| Firebase | Rules, indexes, Auth providers |
| QA | Unit + milestone test plan (doc 07) |

## 11. Risk Register

| Risk | Mitigation |
| --- | --- |
| AI product distortion | Confirm step + fidelity prompts + reject bad outputs |
| Long video gen times | Async jobs + progress states |
| Cost overruns | Plan quotas + rate limits |
| URL scrape blocks | Manual upload fallback |
| DNS delay | Keep *.vercel.app until A-record propagates |

## 12. Definition of Done (per phase)

Feature merged via PR

Unit tests for new pure logic

Logs + errors wired

Preview deploy verified

PRD acceptance notes updated

End of Implementation Plan v1.0